## Cover Page
OSUN STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) & PROGRESS REPORT
State: |  | Osun
Reporting period: |  | FY 2024
SABER Focal Person: |  | Mrs. Yetunde Esan
List of contributing entities: |  |  | Ministry of Economic Planning, Budget and Development, Ministry of Finance, Ministry of Works and Transport, Ministry of Justice, Ministry of Commerce and Industries, Ministry of Cooperatives and Empowerment, Ministry of Lands and Physical planning, Ministry of Science, Innovation and Digital Economy, Osun Internal Revenue Services, Office of Surveyor General and Osun State Investment Promotion Agency.
Link: ???
Is this plan approved by the State Executive Council (SEC) |  |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date:
PEBEC Comments: Please include details of private sector contibutors
Note on A8: ====== ID#AAAAnY4HY2o tc={87C59A12-7B38-4B82-BDAD-C7CFB332BA22} (2023-01-10 16:37:12) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There is a need to indicate reporting period for BERAP and the Progress Report
Note on A10: ====== ID#AAAAnY4HY2s tc={CCD9C3A1-73FA-43B2-9CFF-BE3B1C214680} (2023-01-10 16:37:12) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, clarify if you meant the SABER Focal Person or the SABER Champion

## BERAP
OSUN STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) PROGRESS REPORT
Original action plan as published
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | List of private sector contributors | Budget | Planned Start Date | Planned End Date
1 | Efficiency in property registration and sustainability of the landbased investment process | To Digitize all land titling and property registratioin processes in Osun State by December 2024 | Digitization of Osun Land Titling Process including Osun State Property Acquisition Papers with payable fees activation on webpay system | Property / land application procedure can be started online by the investors, who can also, when appropriate, make payments and receive feedback. Investors can also get information about the milestone they need to reach online. The target is to reduce land tilting and property registration processes to 30-45 days. | Investors and Osun State Government | Permanent Secretary, Ministry of Lands and Physical Planning | Office of Surveyor-General Ministry of science, Innovation and Digital Economy | Solution / Software Developers; Nigerian Institution of Surveyors and Nigeria Bar Association | 100125000 | January, 2024 | March,2024
|  |  | Purchase of modern survey and Land Equipment such as Differential Global positioning System, Leica, 3D laser Scanning Machine and etc) | All tools required to guarantee adherence to any deadline or date mentioned in (i) above are made available. This will improve the delivery of services. | Investors and Osun State Government | Surveyor General, Office of Surveyor General | Ministry of Lands and Physical Planning, Osun Capital Teritory Development Authority, Osun Property Development Corporation | Nigerian Institution of Surveyors | 194852500 | January, 2024 | June,2024
|  | To Provide a robust roadmap for sustainability of the property registration and landbased investment process in Osun State. | Development of Robust Strategic Impelementation Frameworks | Availability of strategic documents will provide adequate roadmap to stakeholders towards sustainability of landbased investment process in Osun State. The target is to develop comprehensive and inclusive operation mannual. | Investors, Osun State Government and General public | Permanent Secretary, Ministry of Lands and Physical Planning | Ministry of Ecoomic Planning, Budget and Development, Osun Property Development Corporation; Osun Capital Teritory Development Authority | Nigerian Institution of Estate Surveyors and Valuers; Nigerian Institution of Town Planners and Nigeria Bar Association | 218785000 | March,2024 | September,2024
2 | Regulatory framework for private investment in fiber optic infrastructure | To strenghtening regulatory framework targetted at boosting Osun State Fibre Option expansion by 80% before December, 2024. | Crafting and Passage of Osun Fiber Optic Bill by the State House of Assembly | Provision of a legal framework for Fibre Option Connectivity in Osun State will greatly improve adoption and community of Practice, this will also provide carrot for adopters while sanctions are awarded to defaulters. The target is to develop an Act that will promote regulatory framework for digital economy and ensure ease of doing business in fiber optic investment. | Investors, Osun State Government and General public | Permanent Secretary, Ministry of Science, Innovation and Digital Economy | Osun State House of Assembly, Ministry of Justice, Ministry of Economic Planning, Budget and Development, Office of the Governor | Association of Telcos in the State Justice Development and Peace Commission of Nigeria | 110000000 | Feb, 2024 | October, 2024
|  |  | Expansion of fiber connectivity in Osun State by 80% on or before December, 2024 | There is a need to encourage relevant TELCOS/ Firms through advocacy targetted at boosting investments in both competitive and less competive geographical location in the State. The target is to ensure 80% Fibre Optic Coverage across the 30 LGAs of the State. | Investors, Osun State Government and General public | Permanent Secretary, Ministry of Science, Innovation and Digital Economy | Ministry of Lands and Physical Planning, Office of Surveyor General | Nigerian Institution of Estate Surveyors and Valuers; Nigerian Institution of Town Planners and Nigeria Bar Association | 1546000000 | 2024-02-01 | Dec, 2024 | NN
OSUN STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) PROGRESS REPORT
3 | Development of an effective PPP framework | To enhance development of an effective PPP framework for Osun State. | Development and deployment of the Public Private Partnership (PPP) legal and institutional framework in Osun State | It is imperative to make available a legal institutional framework that will protect the interests of Private Individuals partnering with government in the business of the State.The target is to make available institutional framework on PPP in the State. | Private Partners (Investors), Osun State Government and General Public | Permanent Secretary, Ministry of Finance | Ministry of Economic Planning, Budget & Development, Office of Development Partners, Public Procurement Agency, Ministry of Justice and House of Assembly. | Nigeria Bar Association, Osun State Branch Legal Aid Council of Nigeria, osun State Network of the Civil Society Organization | 187965500 | February, 2024 | June, 2024
|  |  | Constitution of a High Level Committee on Osun State Public Private Partnerships Coordination | This will serve as a coordinating unit and inter-agency collaboration which is targeted at providing soft-landing for Public Private Partnerships in Osun State | Investors, Osun State Government and General public | Permanent Secretary, Ministry of Finance | Ministry of Economic Planning, Budget & Development, Office of Development Partners, Public Procurement Agency, Ministry of Justice and House of Assembly. | Network of Civil Society Organization | 48050500 | January, 2024 | Aug, 2024
|  |  | Manpower Development on PPP Framework for SABER Thematic MDAs | The staffers of key thematic MDAs are the major drivers of the whole process. Thus, the capacity of these Officers needs to be enhanced. The target here is to train the key staffers of the thematic MDAs within six months. | General Public, Investors and Osun State Government (Policy Makers) | Permanent Secretary, Ministry of Economic Planning, Budget & Development | Ministry of Finance, Osun State Investment Promotion Agency, Ministry of Lands & Physical Planning, Ministry of Commerce and Industries, Ministry Cooperatives & Empowerment, Osun Internal Revenue Service and Osun Public Procurement Agency. | Research Institutions | 68500000 | February,2024 | October,2024
4 | Investment Promotion Environment | To improve Investment Promotion Environment in Osun State targeted at boosting influx of Investor by 75% before Deceber, 2024 | Review and Repeal of Osun Investment Promotion Agency Law | Review of the existing Investment Promotion Agency Law with a view to accomodating emmerging issues and current Invesment Promotion realities and to make the State Investors Friendly. The target is to complete the review of the law before June, 2024 and ensure its componenets complian with national and international standard. | Investors and Osun State Government | Permanent Secretary, Ministry of Commerce and Industries. | Ministry of Cooperatives and Empowerment, Osun State House of Assembly, Ministry of Finance and Ministry of Economic Planning, Budget & Development Osun State Ministry of Justice | Nigeria Bar Association National Association of Small and Medium Enterprises (NASME) Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 38700000 | February, 2024 | June, 2024
|  |  | Rejuvenate the Osun Investment Promotion Agency | The State Government will give a renewed push to the old Osun Investment Promotion Agency to become the Osun Investment Promotion Authority as would be provided for by the review of establishment act. The target here is to improve on ease of doing business. | Unemployed Youths, Investors and Osun State Government | Permanent Secretary, Ministry of Commerce and Industries. | Office of the Governor, Office of the Head of Service, Osun State | Nigeria Bar Association National Association of Small and Medium Enterprises (NASME) Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 106500000 | Jan, 2024 | November, 2024
|  |  | Establishment of Osun Investment Promotion One Stop Shop by October, 2024 | Pooling together a set of related agencies with related activities on promotion of investments in the State is very critical to fastracking documentation process. The target is to improve the ease of doing business in the State. | Investors | Permanent Secretary, Ministry of Commerce, Cooperatives and Industries | Osun State Investment Promotion Authority, Ministry of Finance and Ministry of Economic Planning, Budget and Development | Nigeria Bar Association National Association of Small and Medium Enterprises (NASME) Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 168897500 | March, 2024 | December, 2024
|  |  | Development of Osun Investment Promotiion Authority Website with Backlink to the State Official Website | The openess, transparency and accountability of the whole process need to be proven to the whole World. This will also lead to an increased global engagement. The target here is to have an official web-base presence. | Investors and Osun State Government | Ministry of Commerce, and Industries / Executive Secretary, Osun State Investment Promotion Authority | Ministry of Science, Innnovation and Digital Economy, Ministry of Econmic Planning, Budget and Development | Web Based Solution Providers in Osun State | 52850000 | April, 2024 | October, 2024
|  |  | Establish Osun Investment Promotion Local Business Offices / Federal Constituency | Establishing Osun Investment Promotion Authority Local Business Offices is targeted at: -Provision of support desks to investments / investors in the catchment areas -Ease of cascading invesment releated developments / issues to the Head Office -An assurance of positive commitment to Investors who might have invested in these local areas -Increased Job opportunities for the youths. The target is to establish nine (9) offices in nine (9) Federal constituencies. | Unemployed Youths, Investors and Osun State Government | Executive Secretary, Osun State Investment Promotion Authority | Ministry of Commerceand Industries, Ministry of Local Government and Chieftaincy Affairs | National Association of Small and Medium Enterprises (NASME) Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 136500000 | Feb, 2024 | Aug, 2024
|  |  | Conduct of Osun Investors' Baseline Survey | The availability of a reliable database showcasing the potential investors in the State and their individual area of specialization is critical to development of meaningful economic framework. The target is to have a comprehensive list of investors in the State with their area of interests. | Unemployed Youths, Investors and Osun State Government | Permanent Secretary, Ministry of Commerce and Industries | Minisry of Cooperatives and Empowerment, Osun State Bureau of Statistics, Ministry of Economic Planning, Budget and Development | Research Institutions in the State, National Association of Small and Medium Enterprises (NASME), Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 77850000 | March, 2024 | October, 2024
|  |  | Development of Osun Medium Term Investment Promotion Strategy (MTIPS) | This action is targeted at: - developing a three year rollover strategy to achieve Osun Investment Promotion plan -Eagle view of expected deliverables. -Providing Monitoring and Evaluation mechanisms; -Providing Key Peformance Indicators for performance measurement | General Public, Investors and Osun State Government (Policy Makers) | Executive Secretary, Osun Investment Promotion Agency | Ministry of Econmic Planning, Budget and Development Ministry of Commerce and Industries/ | Research Institutions in the State National Association of Small and Medium Enterprises (NASME) Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 52950000 | March, 2024 | December, 2024
|  |  | Alignment/Mainstreaming of the Osun Investmet Promotion Strategy (MITPS) into the State Medium Term Sector Strategies | This action is targeted at: -Aligning MTIPS with the Osun Long Term Development Plan and Medium Term Sector Strategy towards development of the State | Policy Actors(Government), Investors and General public | Executive Secretary, Osun State Investment Promotion Agency | Ministry of Econmic Planning, Budget and Development | Research Institutions in the State National Association of Small and Medium Enterprises (NASME) Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 21500000 | June, 2024 | September, 2024
|  |  | Automation of Osun Investment Promotion Agency Revenue Generation Portal | This is targeted at: - making payment of revenue easy for Investors; -Blocking revenue leakages through the deployment of USSD codes and other web-based payment technology. | Osun State Government and Investors | Executive Secretary, Osun State Investment Promotion Authority | Ministry of Science, Innovation and Digital Economy, Osun Internal Revenue Service | Web Based Solution Providers in Osun State | 96500000 | March, 2024 | December, 2024
|  |  | Technical Backstop for the Personel on Custormer Realtion Management, Database Development and Management, Global Best Practices in Investors' Relationship Management | This is targeted at equiping the Authority's personnel with effective contemporary technical skills | General Public including Investors | Executive Secretary, Osun State Investment Promotion Authority | National Investment Promotion Council of Nigeria | Research Institutions in Osun State | 28500000 | June, 2024 | December, 2024
|  |  | Conduct Osun Annaul Investment Promotion Performance Review | This is aimed at performance evaluation of set target and deliverables with a view to improving on weaknesses and maintain good speed on strengths | Policy Actors(Government), Investors and General public | Osun State Investment Promotion Authority | Ministry of Econmic Planning, Budget and Development ; Ministry of Commerce and Industries Ministry of Cooperatives and Empowerment | Research Institutions in the State National Association of Small and Medium Enterprises (NASME) Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 38950000 | March, 2024 | December, 2024
5 | Transparency of official fees and procedures | To improve transparency of official fees and procedures while protecting investors from ilegal charges | Establishment of Osun One-Stop-Shop Revenue Base | This is aimed at seemless coordination of all Revenue Generating Agencies (RGSs) in Osun State to be coordinated by the Osun Internal Revenue Services . This drive will provide synergy among all revenue collection agencies in the State. It will also discourage ilegal revenue charges on residents and investors allike | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Permanent Secretaries: Ministry of Economic Planning, Budget and Developemnt Ministry of Commerce, Cooperatives and Industry Ministry of Justice | Revenue Soluton Providers | 15550000 | March, 2024 | August, 2024
|  |  | Baseline Assessment of the State Revenue Web Portal and Automation of Fees and Fines payable to the State Government | This is targeted at blockage of revenue leakages and sharp practices by Officials. It is also targeted at providing transparent view to all Stakeholders on the inflows and remittances | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Ministry of Innovation, Science and Digital Economy | Back End Data Analysts and Solution Providers in the State | 11580000 | March, 2024 | August, 2024
|  |  | Publication of Tax and Fees Manual | Aimed at providing investors with the right educations and information on Official fees and payment procedures in the State | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Osun State Broadcasting Corporation | Civil Society Organizations in the State | 10050000 | March, 2024 | August, 2024
|  |  | Establishment of Revenue Redress Unit /Small Claim Courts | This is targeted at Investors or any resident of the State to easily provide feedbacks andnot only timely but lasting resolution of IGR related grieviances | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Ministry of Justice, Osun State House of Assembly | Nigeria Bar Association | 29500000 | March, 2024 | August, 2024
|  |  | Capacity Building on Grieviance Redress Mechanisms | This is aimed at equiping personnel with the right skills in Revenue related Conflict Resolutioin | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Ministry of Economic Planning, Budget and Development | Civil Society Organizations in the State | 22577800 | June, 2024 | December, 2024
|  |  | Public Relation including BBC Materials | This is aimed at improving procedural transparency of collection and payment of official fees in the State. | Investors, Osun State Government and General public | Executive Secretary, Osun State Investment Promotion Authority | Osun State Ministry of Information & Public Enlightenment | Association of Private Media Practitioners in Osun State | 18500000 | March, 2024 | August, 2024
6 | Transparency of fees and levies for interstate trade and increased exporter certification | To strengthen investors'trust in the State while improving domestic and external trade competitiveness in Osun State | Upgrading of Osun Dry Port by December, 2024 | The need to enhance the revenue acruing to the State and boost economic activities cannot be over emphasized through an upgraded dry port located within the State.The target here is to further boosting revenue through dry port clearing levies and dues. | Investors, Unemployed Youths and Government (National, State and Local) | Permanent Secretary, Ministry of Commerce and Industries | Ministry of Agricuture and Food Security | Research Institutions in the State National Association of Small and Medium Enterprises (NASME) Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 122000000 | March, 2024 | December, 2024
|  |  | Domestication of National produce Law of 1963 and Review of Osun Produce law 2002. | The interest of investors (local and international) as well as that of the Government needs to be protected through a formidable framework. The target is to have a coordinated regulatory framework for produce activities in the State. | Policy Actors(Government), Investors, Produce Marchants, Produce Storekeepers, Produce Processors, Farmers, Hawlage Service Providers | Permanent Secretary, Ministry of Agricuture and Food Security | Ministry of Justice Osun State House of Assembly | All Farmers Association of Nigeria (AFAN), Civil Society Organization, OSUCCIMA, NASSI, NASME Nigeria Bar Association | 25500000 | March, 2024 | December, 2024
|  |  | Optimization of Baorder Control Revenue Generation July 2024 | Introduction of Technology into the Operations of the Osun Board Control Unit would avail the State an opportunity to improve its services to investors and also ensure transparency in revenue generation | Investors, Produce Marchants, Produce Storekeepers, Produce Processors, Farmers, Hawlage Service Providers | Permanent Secretary, Ministry of Agricuture and Food Security | Ministry of Science, Innovation and Digital Economy | All Farmers Associations of Nigeria (AFAN),Osun State Branch, Civil Society Organization Nigeria Bar Association Community Development Associations | 578425500 | March, 2024 | December, 2024
|  |  | Publication of Export labelled Products and Osun Exportation Agreement with approved fees by March, 2024 | This is targeted at building trust with the Investor and also to dicourage sharp practices by officials | Investors, MSME, Organized Private Sector | Permanent Secretary, Ministry of Commerce and Industries | Ministry of Agricuture and Food Security | All Farmers Association of Nigeria (AFAN), Private Sector Media Practioners in Osun State | 39865208 | January, 2024 | June, 2024
7 | State and local business tax regimes | To simplify state and local business tax regimes by making payment easy for taxpayers, dicouraging multiple taxation while widening the Tax net up to 50% by July, 2024 | Tax Payers Database Review | This is targeted at understanding the current situation of tax payers and revenue collections in the State | State Government | Chairman, Osun Internal Revenue Services | Ministry of Economic Planning, Budget and Development | Web Based Data Analysts and Solution Providers | 16500000 | March, 2024 | December, 2024
|  |  | Wideniing of Osun Tax Payers Net by July 2024 | Aimed at widening the tax net by bringing in more Business owners into the tax database of the State | Policy Actors(Government), and Unemployed Youths | Chairman, Osun Internal Revenue Services | Osun State Bureau of Statistics | Research Institutions in the State | 44500000 | March, 2024 | December, 2024
|  |  | Enhancement of the Osun Revenue Services Website | Targeted at providing up to date information about fees and fines in the State. Also make the integrated webpay interphase user friendly. | Policy Actors(Government), and Investors | Chairman, Osun Internal Revenue Services | Ministry of Innovation, Science and Digital Economy | Web Based Data Analysts and Solution Providers | 22600000 | March, 2024 | December, 2024
|  |  | Deployment of Osun Tax Payers App on the Google Playstore and Apple AppStore by August 2024 | Aimed at mobile (Android and Apple) Users for ease of payment of fees and fines | Investors and General public - Organized Private Sector and Micro, Small and Medium Enterprises | Chairman, Osun Internal Revenue Services | Ministry of Innovation, Science and Digital Economy | Web Based Data Analysts and Solution Providers | 33500000 | March, 2024 | December, 2024
|  |  | Deployment of Osun Tax Payers Short Codes | This is targetted at making payment of tax easy anywhere and without the stress of going to the bank | Investors and other tax Payers | Chairman, Osun Internal Revenue Services | Ministry of Economic Planning, Budget and Development | Web Based Data Analysts and Solution Providers | 18000000 | March, 2024 | December, 2024
|  |  | Recruitment of Local Government Resident Revnue Agents in all 30 Local Government Areas of the State | This activity seeks to provide employment opportunities for Locals and also improve tax collection from State and Local Businesses | Unemployed Youths, Investors and Osun State Government | Chairman, Osun Internal Revenue Services | Bureau of Human Resources and Capacity Building | Research Institutions in the State National Association of Small and Medium Enterprises (NASME) Osun State Chambers of Commerce, Industry, Mines and Agriculture National Association of Small Scale Industrialist (NASSI) | 26500000 | June, 2024 | December, 2024
|  |  | Tax Holiday for New Business | This is aimed at encouraging influx of new investors into the State with a view on an emnhanced long term revenue generation | Investors, OPS and MSME | Osun Internal Revenue Services | Office of The Governor | Civil Society Organization | 35000000 | March, 2024 | June, 2024
8 | Quick determination of commercial disputes | To promptly determine and mitigate commercial disputes in Osun State | Establishment of Small Claim Courts in three Senatorial Districts of Osun State | The State is proposing to set up Small Claim Courts in three Senatorial Districts of Osun State to fastrack settlement of commercial disputes as well as other related litigation that might require quick justice delivery | Investors, Land Owners and Government | Chief Justice, High Court of Justice | Ministry of Justice, Ministry of Commerce and Industries | Nigeria Bar Association , Osun Chambers of Commerce, Industry, Mines & Agriculture (OSUCCIMA), National Association of Small Scale Industrialists (NASSI), National Association of Small and Medium Enterprises (NASME) | 278550000 | February, 2024 | December, 2024
|  |  | Commercial Disputes Laws Review/Repeal and Formulation | A reliable institutional framework that will encompass and protect the interests of all relevant key stakeholders in the commercial activites across the State needs to be enshrined. The target here is to provide easy access to justice through a fastrack legal system. | General public | Permanent Secretary, Ministry of Justice | House of Assembly, Ministry of Economic Planning, Budget and Development, House of Assembly | Nigeria Bar Association , Osun Chambers of Commerce, Industry, Mines & Agriculture (OSUCCIMA), National Association of Small Scale Industrialists (NASSI), National Association of Small and Medium Enterprises (NASME) | 29505000 | March, 2024 | December, 2024
|  |  | Grand Total | [5 empty] | 4672179508

## Progress Report
OSUN STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) PROGRESS REPORT
Original action plan as published | [10 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps | PEBEC Comments Please delete this column after update
1 | Efficiency in property registration and sustainability of the landbased investment process | To Digitize all land titling and property registratioin processes in Osun State by December 2024 | Digitization of Osun Land Titling Process including Osun State Property Acqisition Papers with payable fees activation on webpay system | Property / land application procedure can be started online by the investors, who can also, when appropriate, make payments and receive feedback. Investors can also get information about the milestone they need to reach online. The target is to reduce land tilting and property registration processes to 30-45 days. | Investors and Osun State Government | Permanent Secretary, Ministry of Lands and Physical Planning | Office of Surveyor-General Ministry of science, Innovation and Digital Economy | 100125000 | January, 2024 | March,2024 | New | Critical | Activation of action steps | This sheet is not required for 2024 BERAP
|  |  | Purchase of modern survey and Land Equipment such as Differential Global positioning System, Leica, 3D laser Scanning Machine and etc) | All tools required to guarantee adherence to any deadline or date mentioned in (i) above are made available. This will improve the delivery of services. | Investors and Osun State Government | Surveyor General, Office of Surveyor General | Ministry of Lands and Physical Planning, Osun Capital Teritory Development Authority, Osun Property Development Corporation | 194852500 | January, 2024 | June,2024 | On-going | High Impact | Activation of action steps
|  | To Provide a robust roadmap for sustainability of the property registration and landbased investment process in Osun State. | Development of Robust Strategic Impelementation Frameworks | Creating an enabling environment for the whole process to thrive is critical to the success of the various commitment to the programme. Availability of strategic documents will provide adequate guidelines to stakeholders and would-be investors most especially, the implementing MDAs on the actions/activities that need to be taken towards sustainability of landbased investment process in Osun State. The target is to develop comprehensive and inclusive frameworks by September, 2024. | Investors, Osun State Government and General public | Permanent Secretary, Ministry of Lands and Physical Planning | Ministry of Ecoomic Planning, Budget and Development, Osun Property Development Corporation; Osun Capital Teritory Development Authority | 218785000 | March,2024 | September,2024 | New | Critical | Activation of action steps
2 | Regulatory framework for private investment in fiber optic infrastructure | To strenghtening regulatory framework targetted at boosting Osun State Fibre Option expansion by 80% before December, 2024. | Crafting and Passage of Osun Fiber Optic Bill by the State House of Assembly | Provision of a legal framework for Fibre Option Connectivity in Osun State will greatly improve adoption and community of Practice, this will also provide carrot for adopters while sanctions are awarded to defaulters. The target is to develop an Act that will promote regulatory framework for digital economy and ensure ease of doing business in fiber optic investment. | Investors, Osun State Government and General public | Permanent Secretary, Ministry of Science, Innovation and Digital Economy | Osun State House of Assembly, Ministry of Justice, Ministry of Economic Planning, Budget and Development, Office of the Governor | 110000000 | Feb, 2024 | October, 2024 | New | Critical | Activation of action steps
|  |  | Expansion of fiber connectivity in Osun State by 80% on or before December, 2024 | There is a need to encurougae TELCOs and related firms to boost investments in both competitive and less competive geographical location in the State through provision of fiber optic connections across the length and breadth of the State. Meanwhile, properties pwmers whose assets will be affected by these activities must be compensated. The target is to expand fibre optic to at least 80% of LGAs of the State, | Investors, Osun State Government and General public | Permanent Secretary, Ministry of Science, Innovation and Digital Economy | Ministry of Lands and Physical Planning, Office of Surveyor General | 1546000000 | 2024-02-01 | Dec, 2024 | New | Critical | Activation of action steps
3 | Development of an effective PPP framework | To enhance development of an effective PPP framework for Osun State. | Development and deployment of the Public Private Partnership (PPP) legal and institutional framework in Osun State | It is imperative to note that Private Sector Intervention in public investment cannot be overemphasised as the volume of expectations from Government is growing geometrically. The target is to create seamless platform towards implementation of SABER'S activities through PPP Framework. It as well promotes synegy between government and private partners in the economic development of the State (i.e. social-Economic inclusiveness). Privae Firms can leverage this PPP opportunity to promote their investment interest in Osun State. However, the main target here is to finalize PPP legal framework by June, 2024. | Private Partners (Investors), Osun State Government and General Public | Permanent Secretary, Ministry of Finance | Ministry of Economic Planning, Budget & Development, Office of Development Partners, Public Procurement Agency, Ministry of Justice and House of Assembly. | 187965500 | February, 2024 | June, 2024 | New | Critical | Activation of action steps
|  |  | Constitution of a High Level Committee on Osun State Public Private Partnerships Coordination | This will serve as a coorditing unit and inter-agency collaboration which is targeted at providing soft-landing for Public Private Partnerships in Osun State | Investors, Osun State Government and General public | Permanent Secretary, Ministry of Finance | Ministry of Economic Planning, Budget & Development, Office of Development Partners, Public Procurement Agency, Ministry of Justice and House of Assembly. | 48050500 | January, 2024 | Aug, 2024 | New | Critical | Activation of action steps
|  |  | Manpower Development on PPP Framework for SABER Thematic MDAs: | There is critical needs to build the capacity of personnel on implementation of legal framework and operationalisation of guidelines manual to ensure effective implementation of SABER'S activities through PPP. The target here is to conduct trainning sessions for key staff within six months. | General Public, Investors and Osun State Government (Policy Makers) | Permanent Secretary, Ministry of Economic Planning, Budget & Development | Ministry of Finance, Osun State Investment Promotion Agency, Ministry of Lands & Physical Planning, Ministry of Commerce and Industries, Ministry Cooperatives & Empowerment, Osun Internal Revenue Service and Osun Public Procurement Agency. | 68500000 | February,2024 | October,2024 | On-Going | Critical | Activation of action steps
4 | Investment Promotion Environment | To improve Investment Promotion Environment in Osun State targeted at boosting influx of Investor by 75% before Deceber, 2024 | Review and Repeal of Osun Investment Promotion Agency Law | Review of the existing Investment Promotion Agency Law with a view to accomodating emmerging issues and current Invesment Promotion realities and to make the State Investors Friendly. The target is to complete the review of the law before June, 2024 and ensure its componenets complian with national and international standard. | Investors and Osun State Government | Permanent Secretary, Ministry of Commerce and Industries. | Ministry of Cooperatives and Empowerment, Osun State House of Assembly, Ministry of Finance and Ministry of Economic Planning, Budget & Development Osun State Ministry of Justice | 38700000 | February, 2024 | June, 2024 | New | Critical | Activation of action steps
|  |  | Rejuvenate the Osun Investment Promotion Agency | The State Government will give a renewed push to the old Osun Investment Promotion Agency to become the Osun Investment Promotion Authority as would be provided for by the review of establishment act. The target here is to improve on ease of doing business. | Unemployed Youths, Investors and Osun State Government | Permanent Secretary, Ministry of Commerce and Industries. | Office of the Governor, Office of the Head of Service, Osun State | 106500000 | Jan, 2024 | November, 2024 | New | Critical | Activation of action steps
|  |  | Establishment of Osun Investment Promotion One Stop Shop by October, 2024 | This is targeted at bringing all agencies on investment promotion under one roof for ease access to registration and other investment matters by would-be investors in the State. The target is to improve the ease of doing business. | Investors | Permanent Secretary, Ministry of Commerce, Cooperatives and Industries | Osun State Investment Promotion Authority, Ministry of Finance and Ministry of Economic Planning, Budget and Development | 168897500 | March, 2024 | December, 2024 | New | Critical | Activation of action steps
|  |  | Development of Osun Investment Promotiion Authority Website with Backlink to the State Official Website | Needless to say, the State Investment Promotion Agency needs to make web presence if the right set of investors would be able to identify and locate the agency globally. The operation of this agency is propelled to be in hybrid form thereby comprising both public and private work emvironment features. The webpage would increase patronage and quick access locally and internationally | Investors and Osun State Government | Ministry of Commerce, and Industries / Executive Secretary, Osun State Investment Promotion Authority | Ministry of Science, Innnovation and Digital Economy, Ministry of Econmic Planning, Budget and Development | 52850000 | April, 2024 | October, 2024 | New | Critical | Activation of action steps
|  |  | Establish Osun Investment Promotion Local Business Offices / Federal Constituency | Establishing Osun Investment Promotion Authority Local Business Offices is targeted at: -Provision of support desks to investments / investors in the catchment areas -Ease of cascading invesment releated developments / issues to the Head Office -An assurance of positive commitment to Investors who might have invested in these local areas -Increased Job opportunities for the youths. The target is to establish nine (9) offices in nine (9) Federal constituencies. | Unemployed Youths, Investors and Osun State Government | Executive Secretary, Osun State Investment Promotion Authority | Ministry of Commerceand Industries, Ministry of Local Government and Chieftaincy Affairs | 136500000 | Feb, 2024 | Aug, 2024 | New | Critical | Activation of action steps
|  |  | Conduct of Osun Investors' Baseline Survey | Targeted at: -Understanding where the State is currently standing in the investment / investors space; -Provision of an avenue for comparing attainment of milestones -Establiment and validation of take-off Investors Database | Unemployed Youths, Investors and Osun State Government | Permanent Secretary, Ministry of Commerce and Industries | Minisry of Cooperatives and Empowerment, Osun State Bureau of Statistics, Ministry of Economic Planning, Budget and Development | 77850000 | March, 2024 | October, 2024 | New | Critical | Activation of action steps
|  |  | Development of Osun Medium Term Investment Promotion Strategy (MTIPS) | This action is targeted at: - developing a three year rollover strategy to achieve Osun Investment Promotion plan -Eagle view of expected deliverables. -Providing Monitoring and Evaluation mechanisms; -Providing Key Peformance Indicators for performance measurement | General Public, Investors and Osun State Government (Policy Makers) | Executive Secretary, Osun Investment Promotion Agency | Ministry of Econmic Planning, Budget and Development Ministry of Commerce and Industries/ | 52950000 | March, 2024 | December, 2024 | New | Critical | Activation of action steps
|  |  | Alignment/Mainstreaming of the Osun Investmet Promotion Strategy (MITPS) into the State Medium Term Sector Strategies | This action is targeted at: -Aligning MTIPS with the Osun Long Term Development Plan and Medium Term Sector Strategy towards development of the State | Policy Actors(Government), Investors and General public | Executive Secretary, Osun State Investment Promotion Agency | Ministry of Econmic Planning, Budget and Development | 21500000 | June, 2024 | September, 2024 | New | Critical | Activation of action steps
|  |  | Automation of Osun Investment Promotion Agency Revenue Generation Portal | This is targeted at: - making payment of revenue easy for Investors; -Blocking revenue leakages | Osun State Government and Investors | Executive Secretary, Osun State Investment Promotion Authority | Ministry of Science, Innovation and Digital Economy, Osun Internal Revenue Service | 96500000 | March, 2024 | December, 2024 | New | Critical | Activation of action steps
|  |  | Technical Backstop for the Personel on Custormer Realtion Management, Database Development and Management, Global Best Practices in Investors' Relationship Management | This is targeted at equiping the Authority's personnel with effective contemporary technical skills | General Public including Investors | Executive Secretary, Osun State Investment Promotion Authority | National Investment Promotion Council of Nigeria | 28500000 | June, 2024 | December, 2024 | New | Critical | Activation of action steps
|  |  | Conduct Osun Annaul Investment Promotion Performance Review | This is aimed at performance evaluation of set target and deliverables with a view to improving on weaknesses and maintain good speed on strengths | Policy Actors(Government), Investors and General public | Osun State Investment Promotion Authority | Ministry of Econmic Planning, Budget and Development ; Ministry of Commerce and Industries Ministry of Cooperatives and Empowerment | 38950000 | March, 2024 | December, 2024 | New | Critical | Activation of action steps
5 | Transparency of official fees and procedures | To improve transparency of official fees and procedures while protecting investors from ilegal charges | Establishment of Osun One-Stop-Shop Revenue Base | This is aimed at seemless coordination of all Revenue Generating Agencies (RGSs) in Osun State to be coordinated by the Osun Internal Revenue Services . This drive will provide synergy among all revenue collection agencies in the State. It will also discourage ilegal revenue charges on residents and investors allike | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Permanent Secretaries: Ministry of Economic Planning, Budget and Developemnt Ministry of Commerce, Cooperatives and Industry Ministry of Justice | 15550000 | March, 2024 | August, 2024 | Oogoing | Critical | Activation of action steps
|  |  | Baseline Assessment of the State Revenue Web Portal and Automation of Fees and Fines payable to the State Government | This is targeted at blockage of revenue leakages and sharp practices by Officials. It is also targeted at providing transparent view to all Stakeholders on the inflows and remittances | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Ministry of Innovation, Science and Digital Economy | 11580000 | March, 2024 | August, 2024 | New | Critical | Activation of action steps
|  |  | Publication of Tax and Fees Manual | Aimed at providing investors with the right educations and information on Official fees and payment procedures in the State | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Osun State Broadcasting Corporation | 10050000 | March, 2024 | August, 2024 | New | Critical | Activation of action steps
|  |  | Establishment of Revenue Redress Unit /Small Claim Courts | This is targeted at Investors or any resident of the State to easily provide feedbacks andnot only timely but lasting resolution of IGR related grieviances | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Ministry of Justice, Osun State House of Assembly | 29500000 | March, 2024 | August, 2024 | New | Critical | Activation of action steps
|  |  | Capacity Building on Grieviance Redress Mechanisms | This is aimed at equiping personnel with the right skills in Revenue related Conflict Resolutioin | Investors, Osun State Government and General public | Chairman, Osun Internal Revenue Services | Ministry of Economic Planning, Budget and Development | 22577800 | June, 2024 | December, 2024 | Ongoing | Critical | Activation of action steps
|  |  | Public Relation including BBC Materials | This is aimed at improving procedural transparency of collection and payment of official fees in the State. | Investors, Osun State Government and General public | Executive Secretary, Osun State Investment Promotion Authority | Osun State Ministry of Information & Public Enlightenment | 18500000 | March, 2024 | August, 2024 | Ongoing | Critical | Activation of action steps
6 | Transparency of fees and levies for interstate trade and increased exporter certification | To strengthen investors'trust in the State while improving domestic and external trade competitiveness in Osun State | Upgrading of Osun Dry Port Authority by December, 2024 | Aimed at: - decongesting the Sea Port and provide ease of Clearing for Importers / Investor -Reducing the cost of bringing Imported items to the destination where importers might need them -Improving the IGR of the State | Investors, Unemployed Youths and Government (National, State and Local) | Permanent Secretary, Ministry of Commerce and Industries | Ministry of Agricuture and Food Security | 122000000 | March, 2024 | December, 2024 | New | Critical | Activation of action steps
|  |  | Domestication of National produce Law of 1963 and Review of osun Produce law 2002. | The review is targeted at acommodating and current realities in the establishment and operations of the Osun Produce Board with the main focus on Premium Certification for Export labelled products | Policy Actors(Government), Investors, Produce Marchants, Produce Storekeepers, Produce Processors, Farmers, Hawlage Service Providers | Permanent Secretary, Ministry of Agricuture and Food Security | Ministry of Justice Osun State House of Assembly | 25500000 | March, 2024 | December, 2024 | New | Critical | Activation of action steps
|  |  | Optimization of Baorder Control Revenue Generation July 2024 | Introduction of Technology into the Operations of the Osun Board Control Unit would avail the State an opportunity to improve its services to investors and also ensure transparency in revenue generation | Investors, Produce Marchants, Produce Storekeepers, Produce Processors, Farmers, Hawlage Service Providers | Permanent Secretary, Ministry of Agricuture and Food Security | Ministry of Science, Innovation and Digital Economy | 578425500 | March, 2024 | December, 2024 | New | Critical | Activation of action steps
|  |  | Publication of Export labelled Products and Osun Exportation Agreement with approved fees by March, 2024 | This is targetted at building trust with the Investor and also to dicourage sharp practices by officials | Investors, MSME, Organized Private Sector | Permanent Secretary, Ministry of Commerce and Industries | Ministry of Agricuture and Food Security | 39865208 | January, 2024 | June, 2024 | New | Critical | Activation of action steps
7 | State and local business tax regimes | To simplify state and local business tax regimes by making payment easy for taxpayers, dicouraging multiple taxation while widening the Tax net up to 50% by July, 2024 | Tax Payers Database Review | This is targeted at understanding the current situation of tax payers and revenue collections in the State | State Government | Chairman, Osun Internal Revenue Services | Ministry of Economic Planning, Budget and Development | 16500000 | March, 2024 | December, 2024 | Ongoing | Critical | Activation of action steps
|  |  | Wideniing of Osun Tax Payers Net by July 2024 | Aimed at widening the tax net by bringing in more Business owners into the tax database of the State | Policy Actors(Government), and Unemployed Youths | Chairman, Osun Internal Revenue Services | Osun State Bureau of Statistics | 44500000 | March, 2024 | December, 2024 | Ongoing | Critical | Activation of action steps
|  |  | Enhancement of the Osun Revenue Services Website | Targeted at providing up to date information about fees and fines in the State. Also make the integrated webpay interphase user friendly. | Policy Actors(Government), and Investors | Chairman, Osun Internal Revenue Services | Ministry of Innovation, Science and Digital Economy | 22600000 | March, 2024 | December, 2024 | Ongoing | Critical | Activation of action steps
|  |  | Deployment of Osun Tax Payers App on the Google Playstore and Apple AppStore by August 2024 | Aimed at mobile (Android and Apple) Users for ease of payment of fees and fines | Investors and General public - Organized Private Sector and Micro, Small and Medium Enterprises | Chairman, Osun Internal Revenue Services | Ministry of Innovation, Science and Digital Economy | 33500000 | March, 2024 | December, 2024 | Ongoing | Critical | Activation of action steps
|  |  | Deployment of Osun Tax Payers Short Codes | This is targetted at making payment of tax easy anywhere and without the stress of going to the bank | Investors and other tax Payers | Chairman, Osun Internal Revenue Services | Ministry of Economic Planning, Budget and Development | 18000000 | March, 2024 | December, 2024 | Ongoing | Critical | Activation of action steps
|  |  | Recruitment of Local Government Resident Revnue Agents in all 30 Local Government Areas of the State | This activity seeks to provide employment opportunities for Locals and also improve tax collection from State and Local Businesses | Unemployed Youths, Investors and Osun State Government | Chairman, Osun Internal Revenue Services | Bureau of Human Resources and Capacity Building | 26500000 | June, 2024 | December, 2024 | Ongoing | Critical | Activation of action steps
|  |  | Tax Holiday for New Business | This is aimed at encouraging influx of new investors into the State with a view on an emnhanced long term revenue generation | Investors, OPS and MSME | Osun Internal Revenue Services | Office of The Governor | 35000000 | March, 2024 | June, 2024 | Ongoing | Critical | Activation of action steps
8 | Quick determination of commercial disputes | To promptly determine and mitigate commercial disputes in Osun State | Establishment of Small Claim Courts in three Senatorial Districts of Osun State | The State is proposing to set up Small Claim Courts in three Senatorial Districts of Osun State to fastrack settlement of commercial disputes as well as other related litigation that might require quick justice delivery | Investors, Land Owners and Government | Chief Justice, High Court of Justice | Ministry of Justice, Ministry of Commerce and Industries | 278550000 | February, 2024 | December, 2024 | New | Critical | Activation of action steps
|  |  | Commercial Disputes Laws Review/Repeal and Formulation | This to accommodate all the business related emrging issues due to changes in our environment which the old laws could not address. | General public | Permanent Secretary, Ministry of Justice | House of Assembly, Ministry of Economic Planning, Budget and Development, House of Assembly | 29505000 | March, 2024 | December, 2024 | New | Critical | Activation of action steps
|  |  | Grand Total |  |  |  |  | 4672179508